## GeneralPlan
	Motivation	To meet the future need of the Turkish Aerospace in developing hypersonic aerospace vehicles

	Objective	Developing a transient, compressible, two-temperature, 3D, Implicit semi-coupled, thermochemical non-equilibrium hypersonic CFD solver. This solver shall be able applicable in the continuum-transition regime (1.0 > Knudsen number > 0.2).

	Scope	OpenFOAM will be the development platform, tamsAero will be used for solving the conservative variables (rho rhoU rhoE) as a coupled system, whereas the turbulence model, the second temperature equation and the specie transport equations will be solved sequentially. Furthermore, the chemical reactions will be handled akin to the reactingFoam capabilities. The ionization processes are not considered since the electronic energy mode is omitted.

Task No	Task Description	Semester 1				Summer Break			Semester 2				Semester 3				Summer Break			Semester 4
1	Understanding the governing equations, and the required computational sub-modules
2	Listing the required modifications/new implementations for each part of the code
3	Deciding the solver execution sequence and the code integration methods with sub-modules
4	Chemical reactions (Implementing them separately (Isolating this part from reactingFoam) & unit testing)
5	Specie transport equations [rho_s, for each s] (Implementing them separately (Isolating this part from reactingFoam) & unit testing)
6	New thermodynamic library (Implementation & unit testing)
7	Vibration energy equations [rhoE_v_m for each m], convection, diffusion and source terms (Implementation & unit testing)
8	Conserved variables (rho rhoU rhoE) part: For instance, modifying the viscous flux in the energy equation, Dalton’s law etc.
9	Integrating all the sub-parts of the code
10	Validating the solver, comparisons with experimental and numerical (SU2_NEMO, Eilmer etc.) results
11	Publication (paper & thesis)

## Semester1
		Motivation	Understanding the governing equations, and the required computational sub-modules alongside listing the required modifications/new implementations for each part of the code

		Objective	Developing pretty-well understanding of governing equations, capability to read OpenFOAM solver source code, consuming all of the noteworthy literature about external flow solvers with chemical reactions in OpenFOAM, and creating modifications/implementations list of the TAMS-AERO code

		Start Date	17.02.2025					End Date			23.06.2025

Sub Task No	Main Task Description	Sub Task Description	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18
1	Understanding the governing equations, and the required computational sub-modules	Overall literature study for relevant open source for hy2Foam
2		Selection and compilation of the relevant open source hy2Foam
3		Overall literature study for relevant open source Eilmer
4		Selection and compilation of the relevant open source Eilmer
5		Overall literature study for relevant open source SU2-NEMO
6		Selection and compilation of the relevant open source SU2-NEMO
7		Test Case Simulations for hy2Foam, Eilmer, SU2-NEMO
8		Examination of implementation of chemical reactions within the relevant solvers
9	Listing the required modifications/new implementations for each part of the code	Literature study of hyperReactingFoam and possible relevant open source CFD solvers
10		Compilation and examination of the selected solver
11		Extracting the implementation/modification list out of selected solver

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits

## TestCases
		Motivation	Understanding the governing equations, and the required computational sub-modules alongside listing the required modifications/new implementations for each part of the code

		Objective	Developing pretty-well understanding of governing equations, capability to read OpenFOAM solver source code, consuming all of the noteworthy literature about external flow solvers with chemical reactions in OpenFOAM, and creating modifications/implementations list of the TAMS-AERO code

		Start Date	17.02.2025					End Date			23.06.2025

Sub Task No	Main Task Description	Sub Task Description	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18
1	Test Case Simulations for hy2Foam	Pre-processing of Test Cases
2		Vibrational-Translational Relaxation of a Single-Species Gas in Adiabatic Heat-Bath
3		Vibrational-Translational Relaxation of a non-Reacting N2-N Mixture in Adiabatic Heat-Bath
4		Vibrational-Translational Relaxation of a non-Reacting N2-O2 Mixture in Adiabatic Heat-Bath
5		Relaxation of a Chemically Reacting N2-N Mixture in Adiabatic Heat-Bath
6		Relaxation of Chemically Reacting Air in Adiabatic Heat-Bath
7		Vibrational-Translational Relaxation of non-Reacting N2 on Blunted Cone
8		Relaxation of Chemically Reacting Air on Double-Wedge
9	Test Case Simulations for Eilmer	Pre-processing of Test Cases
10		Vibrational-Translational Relaxation of a Single-Species Gas in Adiabatic Heat-Bath
11		Vibrational-Translational Relaxation of a non-Reacting N2-N Mixture in Adiabatic Heat-Bath
12		Vibrational-Translational Relaxation of a non-Reacting N2-O2 Mixture in Adiabatic Heat-Bath
13		Relaxation of a Chemically Reacting N2-N Mixture in Adiabatic Heat-Bath
14		Relaxation of Chemically Reacting Air in Adiabatic Heat-Bath
15		Vibrational-Translational Relaxation of non-Reacting N2 on Blunted Cone
16		Relaxation of Chemically Reacting Air on Double-Wedge
17	Test Case Simulations for SU2-NEMO	Pre-processing of Test Cases
18		Vibrational-Translational Relaxation of a Single-Species Gas in Adiabatic Heat-Bath
19		Vibrational-Translational Relaxation of a non-Reacting N2-N Mixture in Adiabatic Heat-Bath
20		Vibrational-Translational Relaxation of a non-Reacting N2-O2 Mixture in Adiabatic Heat-Bath
21		Relaxation of a Chemically Reacting N2-N Mixture in Adiabatic Heat-Bath
22		Relaxation of Chemically Reacting Air in Adiabatic Heat-Bath
23		Vibrational-Translational Relaxation of non-Reacting N2 on Blunted Cone
24		Relaxation of Chemically Reacting Air on Double-Wedge

Legend
	Not Started
	Currently
	Completed
	Incompleted within time limits